## Stories
# | Type | Functionality | Possible User Rolls | Description | Story Points | Assigned To
1 | UI | Request Account | Junior, Sernior and Faculty | Create UI (HTML Page) to register account Expecting plain static html page with labels, input fields, action buttons (place holder) Try to accomdate all fields mentioned in "User" table in schema. Acceptance Criteria: A static HTML with all editable fields and action buttons that can be view in browser irrespective of DB connection and service call No validation Expected | 2
2 | UI | Create Junior's Account | Faculty | Ceate UI (HTML Page) to allow Faculty to create Junior's account. Expecting plain static html page with labels, input fields, action buttons (place holder) Try to accomdate all fields mentioned in "User" table in schema. Acceptance Criteria: A static HTML with all editable fields and action buttons that can be view in browser irrespective of DB connection and service call No validation Expected | 2
3 | UI | Manage User Registration | PO (Placement Officer) | Ceate UI (HTML Page) to allow PO to view user details who requsted for registration Expecting plain static html page with read only user information, action buttons (place holder). Acceptance Criteria: A static HTML with all readonly fields and action buttons that can be view in browser irrespective of DB connection and service call No validation Expected Use static JSON data as input | 1
4 | UI | Manage Users | PO (Placement Officer) | Ceate UI (HTML Page) to allow PO to view already registered user's details Expecting plain static html page with read only user information, action buttons (place holder). Acceptance Criteria: A static HTML with all readonly fields and action buttons that can be viewed in browser irrespective of DB connection and service call No validation Expected Use static JSON data as input | 1
5 | UI | Manage Company | PO (Placement Officer) | Create UI (HTML Page) to register/edit company details. Expecting plain static html page with labels, input fields, action buttons (place holder) Try to accomdate all fields mentioned in "Company" table in schema. Acceptance Criteria: A static HTML with all editable fields and action buttons that can be view in browser irrespective of DB connection and service call No validation Expected | 2
6 | UI | View List of data # data-grid (Template for all lists) | common | Create UI (HTML Page) to view list of data Expecting plain static html page Use bootstrap css to creaet grid (table structure) should have working navigation take static input data list First column should be check-box Acceptance Criteria: A static HTML having data grid, check-box for each row, navigation to traverse first, last ,next, previous Page size (number of rows) can be static/fixed The html should be viewed in browser irrespective of DB connection and service call No validation Expected | 5
7 | UI | View List of Users requested for Registration | PO (Placement Officer) | Ceate UI (HTML Page) to view list of users requested for registration. Expecting plain static html page with grid and action buttons at bottom of grid. Use common data-grid, static user list data Acceptance Criteria: A static HTML with data grid and action buttons The HTML page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Register, Delete Request | 1
8 | UI | View List of Users | PO (Placement Officer) | Ceate UI (HTML Page) to view list of users along with there latest role. Expecting plain static html page with grid and action buttons at bottom of grid. Use common data-grid, static user list data Acceptance Criteria: A static HTML with data grid and action buttons The HTML page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Delete, Promote to Senior, Reset Password | 1
9 | UI | View List of Companies | PO (Placement Officer) | Ceate UI (HTML Page) to view list of companies. Expecting plain static html page with grid and action buttons at bottom of grid. Use common data-grid, static company list data Acceptance Criteria: A static HTML with data grid and action buttons The HTML page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Add, Edit, Delete | 1
10 | UI | View Questions & answers and Prrove those | Faculty | Ceate UI (HTML Page) for Faculty to view list of Q&A. Expecting plain static html page with grid and action buttons at bottom of grid. Use common data-grid, static company list data Acceptance Criteria: A static HTML with data grid and action buttons It should show Qustions and respective answers next/below to it. One should able to distinguish the Qustion and its answers. The Faculty should be able to select one or more answers and approve/reject those. The HTML page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Arrove, Reject | 3
11 | UI | View Questions & answers | Senior and Junior | Ceate UI (HTML Page) for senior to view list of Q&A Expecting plain static html page with grid and action buttons at bottom of grid. Use common data-grid, static company list data Acceptance Criteria: A static HTML with data grid and action buttons It should show Qustions and respective approved answers next/below to it. One should be able to distinguish the Qustion and its answers. The HTML page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Raise Question, Post Answer | 2
12 | UI | Raise Question | Junior | Ceate UI (HTML Page) for Junior to raise question. Expecting plain static html page with labels, input fields, drop-down list of companies, action buttons (place holder) Use static data for company list. Acceptance Criteria: A static HTML with company drop-down list, text area for question and other editable fields (if any) and action buttons that can be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Post, Cancel | 2
13 | UI | Post Answer | Senior | Ceate UI (HTML Page) for Senior to post answer. Expecting plain static html page with question(ReadOnly), company name (RO), Requester's name(RO), input field(s), action buttons (place holder) Use static data for question info. Acceptance Criteria: A static HTML with all mentioned ReadOnly fields, text area to post answer and action buttons Page should be viewed in browser irrespective of DB connection and service call No validation Expected Action Buttons: Post, Cancel | 2
14 | UI | Report | Faculty, PO | Will look later If anyone want to work on it without description, welcome :) | 2
Backend APIS
# | Type | API | Input Params | Description | Story Points | Assigned To
1 | GET | GetUserById | userId | Get all user details from DB for given userID | 1
2 | GET | GetUserByLoginName | LoginName | Get all user details from DB for given login name | 1
3 | GET | IsUserExists | LoginName, Email ID | Check if user exists for given login name OR email ID (Any one criteria can be provided) and will return 1 if exist else 0 Note: User login name and email ID will be always unique for active users New request will have validation for login name and email id during submission itself Deleted user will not be removed from system, it will be marked as deleted flag. These are business logic added for information and nothing to do with this API. | 1
4 | GET | GetUserList | Status (DEL/ACT) | Get all users with appropreate status | 2
5 | POST | CreateUser | User details | Creaete user | 2
6 | PUT | UpdateUser | UserId, details | Updates user details | 2
7 | PUT | DeleteUser | UserID | Update user, set status as "DEL" | 1
8 | GET | GetRegistrationById | RegistrationId | Get all user registration details from DB for given RegistrationId | 1
9 | GET | GetRegistrationList | Status (DEL/ACT) | Get list of Registration with appropreate status | 2
10 | POST | CreateRegistration | Registration details | Create Registration | 2
11 | PUT | UpdateRegistrationStatus | RegistrationId, Status | Updates Registration Status (REG, RJC) | 2
12 | GET | GetCompanyByID | CompanyId | Get company details for given company id | 1
13 | GET | GetCompanyList | Status (DEL/ACT) | Get all companies with appropreate status | 2
14 | POST | CreateCompany | company details | Create company | 2
15 | PUT | UpdateCompany | companyId, details | Update company | 2
16 | PUT | DeleteCompany | companyId | Update company, set status as "DEL" | 1
17 | GET | GetQuestionList | Filter criteria (Company Name/ posted by user | Get all companies passes filter criteria | 2
18 | POST | CreateQuestion | Question details | Create Question | 2
19 | PUT | UpdateQuestion | QuestionId, details | Update Question | 2
20 | GET | GetAnswerList | Filter criteria (Company Name/ posted by user/ status) | Get all companies passes filter criteria | 2
21 | POST | CreateAnswer | Answer details | Create Answer, set status "PND" | 2
22 | PUT | UpdateAnswer | AnswerId, details | Update Answer | 2
23 | PUT | ApproveAnswer | AnswerId | Update Answer, set status "APP" | 1
24 | PUT | RejectAnswer | AnswerId, reason | Update Answer, set status "RJC" | 1
Other Stories
Validation
|  | Transform HTML |  | Transform HTML to React component
|  | Responsive |  | Make components to responsive
|  | Dynamic, make REST call |  | Use dynamic data using REST call
|  | Authentication |  | Validate login request
|  | Authorization |  | For each request, action make ROLL based authorization May be we can define roll and access in DB based on available time
|  | Overall Integration |  | It will happen eventually but need to verify at the end
|  | Optimization |  | If time permits
|  | Reports |  | Prepare report query logic, create UI, export functionality
|  | Email Notification |  | If time permits
|  | Forgot/Reset password |  | If time permits, UI will be required RESET PWD can be achieved using ResetPasswordFlag without any complex logic, so that the user has to set password on next login attempt
|  | Missing |  | There could be more things that may be missed, plz add if observed